## Assignment Schedule
Column1 | Start Date | Duration | End Date
Project proposal | Week 3 | 3 weeks | Week 6
Literature review | Week 6 | 2 Weeks | Week 8
Research methodology | Week 10 | 2 Weeks | Week 12
Research Findings | Week 12 | 2 Weeks | Week 14
System Requirements & Specification | Week 16 | 2 Weeks | Week 18
Analysis And Design | Week 18 | 2 Weeks | Week 20
Software Implementation | Week 12 | 9 Weeks | Week 21
Software Testing | Week 20 | 2 Weeks | Week 22
Evaluation | Week 22 | 1 Week | Week 23
Conclusion | Week 23 | 1 Week | Week 24

## Sheet1
Task | Start Date (Week) | Duration(week) | End Date
Project proposal | 3 | 3 | 6
Literature review | 6 | 2 | 8
Research methodology | 10 | 2 | 12
Research Findings | 12 | 2 | 14
System Requirements & Specification | 16 | 2 | 18
Analysis And Design | 18 | 2 | 20
Software Implementation | 12 | 9 | 21
Software Testing | 20 | 2 | 22
Evaluation | 22 | 1 | 23
Conclusion | 23 | 1 | 24